## Sheet1
BUSINESS ENABLING REFORM ACTION PLAN (BERAP) OF CROSS RIVER STATE FOR YEAR 2025
ORIGINAL ACTION PLAN AS PUBLISHED | [11 empty] | PROGRESS UPDATE
S/N | BUSINESS ENABLING REFORM AREAS | REFORM OBJECTIVES | ACTION STEPS | DESCRIPTION AND KEY TARGETS | BENEFICIARIES | RESPONSIBLE MDA | CONTRIBUTING MDAS | LIST OF PRIVATE SECTOR CONTRIBUTORS | ESTIMATED COSTS (N) | PLANNED START DATE | PLANNED END DATE | STATUS | EXPLANATION OF ACTION NOT COMPLETED | NEXT STEPS
1 | Initiate One pilot investment in Agriculture using Cross River State Framework for Responsible and Inclusive Land-Intensive Agriculture model | This initiative will ensure satisfactory implementation of Cross River State Framework for Responsible and Inclusive Land-Intensive Agriculture (FRILIA) with at least 1 pilot investment materialized underCross River State Framework for Responsible and Inclusive Land-Intensive Agriculture CRS FRILIA | 1. Identify specific Intensive Agricultural Investment at minimum large-scale mechanized crop such as cocoa or rice plantation value chain through consultation with relevant stakeholders from government Minitries Department and Agencies, affected Local Government Council, Traditional leaders, Lands Owners and others to implement Cross River State Framework for Responsible and Inclusive Land-Intensive Agriculture pilot project. | Framework for Responsible and Inclusive Land Investment in Agriculture piloted in Cross River State | Cross River State Government, Investors, Host Communities, Local Government Authorities, Traditional rulers, Unions, Land Title holders, traders and general public | Investment Promotion Bureau | Ministry of Lands, CRS Geographic Information Agency, Office of the State Surveyor General, Federal and State Ministries of Environment, CRS Ministries of Agriculture, CRS Land Use Allocation Committee, Ministry of Industry, Ministry of Commerce, Ministry of Local Government Affairs, Department of Chieftaincy Affairs, State Border Commission | Calabar Chambers of Commerce, Industry, Mineral and Agriculture (CALCIMA), Manufacturers Association of Nigeria (MAN) | 200000000 | 5th February 2025 | 10th December 2025 | DELAYED: This reform will ensure satisfactory implementation of Cross River State Framework for Responsible and Inclusive Land-Intensive Investment in Agriculture (FRILIA) with at least 1 pilot investment materialized underCross River State Framework for Responsible and Inclusive Land-Intensive Agriculture CRS FRILIA | Implementation is delayed due to persistent community conflict over farm land title in the area desgnated for the FRILIA pilot project, after the identification of specific Intensive Agricultural Investment at minimum large-scale mechanized crop such as cocoa or rice plantation value chain through consultation with relevant stakeholders from government Minitries Department and Agencies, affected Local Government Council, Traditional leaders, Lands Owners and others to implement Cross River State Framework for Responsible and Inclusive Land-Intensive Agriculture pilot project. | 1. Implementation of adopted published CRS FRILIA guidelines/ toolkits for the Intensive Agricultural Investment Pilot projects implementation in all stages and ensure strict compliance will commcence from August 2026 and concluded in November 2026
2. Implement adopted published CRS FRILIA guidelines/ toolkits for the Intensive Agricultural Investment Pilot project implementation in all stages and ensure strict compliance
2 | Upgrade Cross River State Geographic and Social Data | This initiative will provide explicit geographical and social references about Cross River State to potential investors | 1. Engage professional investment promotion advisors to ascertain specific geographical and social data that will promote Cross River State as a preferred destination for inflow of Foreign Direct Investment and Domestic Direct Investment to the state | CR State Investment Promotion Bureau and State Bureau of Statistic to expand, update and publish State Geographical and social data that will present the state as a preferred destination for Foreign Direct Investment and Domestic Direct Investment | Cross River State Government, Cross River State Investment Promotion Bureau, Investors, organized private sector, Federal Bureau of Statistics | Cross River State Investment Promotion Bureau | State Bureau of Statistics, Cross River State Geographic Information Agency, State Planning Commission, Cross River State Ministry of Education, Cross River State Ministry Social Welfare, Ministry of Wealth Creath Creation, Cross River State Ministry of Solid Minerals, Cross River State Ministry of Tourism, Cross River State Ministry of Tourism and Culture | Calabar Chambers of Commerce, Industry, Mineral and Agriculture (CALCIMA), Manufacturers Association of Nigeria (MAN) | 50000000 | January 15th, 2025 | October 20th, 2025 | DELAYED: This initiative willl provide explicit geographical and social references about Cross River State to potential investors | 1. Report submitted by professional investment promotion advisors to ascertain specific geographical and social data that will promote Cross River State as a preferred destination for inflow of Foreign Direct Investment and Domestic Direct Investment to the state not detailed and objective. 2. Forwarding of recommendations to State Bureau of Statistic to confirm if prescribe data are available in the state data bank, up to date or not delayed as report is not detailed and objective. | 1. Engagement of competent professional investment promotion advisors to ascertain specific geographical and social data that will promote Cross River State as a preferred destination for inflow of Foreign Direct Investment and Domestic Direct Investment to the state to be achieve by August 2026
2. Forwarding of recommendations to State Bureau of Statistic to confirm if prescribe data are available in the state data bank, up to date or not to be achieve by August 2026 3. If not, engage a consultant to provide explicit geographical and social data references about Cross River State to be concluded by September 2026
2. Forward recommendations to State Bureau of Statistic to confirm if prescribe data are available in the state data bank, up to date or not.
|  |  | 3. If not, engage a consultant to provide explicit geographical and social data references about Cross River State. | [9 empty] | 3. Engagement of a consultant to provide explicit geographical and social data references about Cross River State delayed pending consideration of engaging more competent professional investment promotion advisors
3 | Develop active website for Cross River State Lands Cluster MDAs | This initiative will ensure that Lands Cluster MDAs have portals that bear details of their services and can be used for transactions | 1. Engage with Chief Executives of Ministry of Land, Office of the State Surveyor General, Director General CRS Geographic Information Agency on the need to develop an active website to provide detailed information for CRS Land Cluster and online transactions | Ministry of Lands, CRS Geographic Information Agency and Office of the Surveyor General will have active portal that will enable the public to access information on their services, C of O statistics and online transaction | Cross River State Government, General Public, Investors | Cross River State Ministry of Lands | CRS Geographic Information Agency, Office of the State Surveyor General, CRS Ministry of Science and Technology, CRS Investment Promotion Bureau | Calabar Chambers of Commerce, Industry, Mineral and Agriculture (CALCIMA), Manufacturers Association of Nigeria (MAN) | 10000000 | February 10th 2025 | April 20th 2025 | DELAYED : This initiative will ensure that Lands Cluster MDAs have portals that bear details of their services and can be used for transactions | 1. Late approval of funds by the governor delayed the engagement of consultant to develop active website for Ministry of Lands, CRS Geographical Information Agency, Office of the State Surveyor General to provide information on application process for – 1. Construction permits, 2. CofO, Number of C of O issued, and enable online application for Construction permit, C of O, layout approval, etc., after engagement with chief executives of Ministry of Land, Office of the State Surveyor General, Director General CRS Geographic Information Agency on the need to develop an active website to provide detailed information for CRS Land Cluster and online transactions, | 1. Engagement of consultant to develop active website for Ministry of Lands, CRS Geographical Information Agency, Office of the State Surveyor General to provide information on application process for – 1. Construction permits, 2. CofO, Number of C of O issued, and enable online application for Construction permit, C of O, layout approval, etc., after engagement with chief executives of Ministry of Land, Office of the State Surveyor General, Director General CRS Geographic Information Agency on the need to develop an active website to provide detailed information for CRS Land Cluster and online transactions to be achieved by August 2026
2. Late approval of funds by the governor for engagement of consultant to develop active website delayed the training of five (5) personnels from each of the land clusters mentioned in 2 on how to manage the portal platform to be achieved by September 2026 3.Late approval of funds by the governor for the procurement of ICT equipment for the online platforms such as computers, routers, etc. to be achieve by September 2026
|  |  | 2. Engage consultant to develop active website for Ministry of Lands, CRS Geographical Information Agency, Office of the State Surveyor General to provide information on application process for – 1. Construction permits, 2. CofO, Number of C of O issued, and enable online application for Construction permit, C of O, layout approval, etc. | [9 empty] | 2. Late approval of funds by the governor for engagement of consultant to develop active website delayed the training of five (5) personnels from each of the land clusters mentioned in 2 on how to manage the portal platform 3.Late approval of funds by the governor for the procurement of ICT equipment for the online platforms such as computers, routers, etc.
3. Train 5 personnels from each of the land clusters mentioned in 2 on how to manage the portal platform
4. Procurement of ICT equipment for the online platforms such as computers, routers, etc.
4 | Digitized Registered Certificate of Occupancies | This initiative will ensure new CofO registered from 2025 (1st January 2025 to 31st December2025 are digitize and index in accordance with international good practice recognizing female owned or joint/co-owned | 1. Gather manual copies of Certificate of Occupancy issued, Maps and photographs 2. Scan collated documents into a digital format and index in line international best practice 3. Ensure record index are searchable through the internet | Cross River State Geographic Information system to publish online statistics of Certificates of Occupancies registered indicating gender ratio | Cross River State Government, General Public, Investors | Cross River State Geographic Information Agency | Cross River State Ministry of Lands, Land Use Allocation Committee, Office of the State Surveyor General, CRS Internal Revenue Service | Calabar Chambers of Commerce, Industry, Mineral and Agriculture (CALCIMA), Manufacturers Association of Nigeria (MAN) | 50000000 | January 20th 2025 | November 20th 2025 | COMPLETED: This initiative has ensured that new CofO registered from 2025 (1st January 2025 to 31st December2025 are digitize and index in accordance with international good practice recognizing female owned or joint/co-owned | 1.Manual copies of Certificate of Occupancy issued, Maps and photographs gathered. 2. Collated documents scanned into a digital format and index in line international best practice 3. Record index are searchable through the internet | The State will continue to ensure that new CofO registered are digitize and index in accordance with international good practice recognizing female owned or joint/co-owned
5 | Develop active website for Cross River State Infrastructure Safety Regulatory Agency (CRISRA) | This initiative will create a platform for State online publication of ROW Processes and Fees, ROW Transaction and Approved ROW related request | 1. Engage with the Director General/Chief Executive Officer of Cross River State Infrastructure Safety Regulatory Agency (CRISRA) on the need to develop an active portal to provide detailed information on CRS Fiber Infrastructure/ Regulations, ROW Application Process and online transaction | Cross River State Infrastructure Safety Regulatory Agency will have active portal that will enable investors and general public access to detailed information on the State Fiber Infrastructure, Safety, Regulations, Services, online transaction and GRM | Cross River State Government, Investors, organize private sector, General Public | Cross River State Infrastructure Safety Regulatory Agency | CRS Ministry of Science and Technology, CRS Internal Revenue Service, CRS Geographic Information Agency, CRS Ministry of Lands, Office of the State Surveyor General, CRS Enabling Business Environment Council Secretariat | Calabar Chambers of Commerce, Industry, Mineral and Agriculture (CALCIMA), Manufacturers Association of Nigeria (MAN) | 2000000 | February 5th 2025 | March 20th 2025 | DELAYED This initiative will create a platform for State online publication of ROW Processes and Fees, ROW Transaction and Approved ROW related request | 1. Awaiting approval by the governor to engage the services of an ICT expert to develop an active portal for CRISRA for information dissemination and online registration/ documentation after engaging with the Director General/Chief Executive Officer of Cross River State Infrastructure Safety Regulatory Agency (CRISRA) on the need to develop an active portal to provide detailed information on CRS Fiber Infrastructure/ Regulations, ROW Application Process and online transaction | 1. Engage the services of an ICT expert to develop an active portal for CRISRA for information dissemination and online registration/ documentation on August 2026
[13 empty] | 2. Awaiting the approval of the governor to engage the services of an ICT expert to develop an active website for Cross River State Infrastructure Safety Regulatory Agency (CRISRA) before training of an ICT Desk Officer to manage the platform | 2. Train an ICT Desk Officer to manage the platform on September 2026
2. Engage the services of an ICT expert to develop an active portal for CRISRA for information dissemination and online registration/ documentation
[13 empty] | 3. Awaiting the approval of the governor to procure ICT equipment such as computer, router, etc. for the online platform | 3. Procure ICT equipment such as computer, router, etc. for the online platform on September 2026
3. Train an ICT Desk Officer to manage the platform
4. Procure ICT equipment such as computer, router, etc. for the online platform
6 | Publish 10% increase in Fiber deployment in Cross River State | This initiative is aim to ascertain the percentage increase in fiber deployment baseline in Cross River State as of December 31 2025 | 1. Liaise with the Nigerian Communications Commission (NCC) to have NCC obtain GIS maps of their deployed non-GPON fiber from all operators deploying fiber in CRS as of December 31, 2022 in line with WBG/ITU-developed Open Standard for terrestrial optical fiber cable data. | Achieve percentage increase in fiber deployment in Cross River State since December 31st, 2022 to December 31st, 2025 | Cross River State Government, Investors, organize private sector, General Public | CRS Infrastructure Safety Regulatory Agency | Nigerian Communication Commission, Ministry of Lands, State Bureau of Statistics, Office of the State Surveyor General, CRS Geographic Information Agency | Calabar Chambers of Commerce, Industry, Mineral and Agriculture (CALCIMA), Manufacturers Association of Nigeria (MAN) | 10000000 | January 10th 2025 | June 12th 2025 | COMPLETED: This initiative is aim to ascertain the percentage increase in fiber deployment baseline in Cross River State as of December 31 2025 | 1. Commence liaisIng with the Nigerian Communications Commission (NCC) to have NCC obtain GIS maps of their deployed non-GPON fiber from all operators deploying fiber in CRS as of December 31, 2022 in line with WBG/ITU-developed Open Standard for terrestrial optical fiber cable data. | 1. To obtain resulting operator-level maps from NCC (in raw data form as provided by operators to NCC) and calculate 2025 fiber deployment for CRS via overlaying fiber maps against state boundaries, using GIS software to commence form September 2026
2. Calculation of percentage increase in fiber deployment in CRS as of December 31, 2025 (based off combined NCC - State database) vis-à-vis 2022 fiber deployment baseline to commence from september 2026
2. Obtain resulting operator-level maps from NCC (in raw data form as provided by operators to NCC) and calculate 2025 fiber deployment for CRS via overlaying fiber maps against state boundaries, using GIS software
3. Calculate percentage increase in fiber deployment in CRS as of December 31, 2025 (based off combined NCC - State database) vis-à-vis 2022 fiber deployment baseline
7 | Establish State Project Facilitation Fund | This initiative is aim towards setting at minimum 3% of total pipeline estimated capital investment for 3 State PPP project Facilitation. | 1. Obtain approval from the Governor to develop an administrative instrument for establishment of Bakassi Deep Seaport, Calabar Super Highway, Calabar – Obudu Train Project and Marina Resort Project Facilitation Fund with intent to commit minimum of 3% of the pipeline estimated capital investment for development. | The State Government allocate 3% of total pipeline estimated capital as Project Facilitation Fund for all State PPP projects | CRS Government, Investors, General Public | CRS Bureau of Public Private Partnership | CRS Investment Promotion Bureau, State Privatization Council, Governor’s Office, CRS Ministry of Transport, CRS Ministry of Tourism, State Planning Commission, CRS Budget Department, CRS Geographic Information Agency, Office of the State Surveyor General, Ministry of Works | Calabar Chambers of Commerce, Industry, Mineral and Agriculture (CALCIMA), Manufacturers Association of Nigeria (MAN) | 20000000 | February 10th 2025 | June 12th 2025 | COMPLETED This initiative is aim towards setting at minimum 3% of total pipeline estimated capital investment for 3 State PPP project Facilitation. | 1. Approval obtained from the Governor to develop an administrative instrument for establishment of Marina Resort Project Facilitation Fund with intent to commit minimum of 3% of the pipeline estimated capital investment for development. | The State will always establishment Project Facilitation Fund with commitement of minimum of 3% of the pipeline estimated capital investment for all PPP projects
|  |  | 2. Upon approval, engage expert to develop Project Facilitation Fund Business Plan, Rules, Governance, and Operational Manual for above mentioned projects. | [9 empty] | 2. Expert engaged to develop Project Facilitation Fund Business Plan, Rules, Governance, and Operational Manual for above mentioned projects. | .
3.Executive Council approval obtained
4. Published on State Official website
3. Obtain Executive Council approval
4. Publish on State Official website
8 | Reform CRS Investment Promotion Bureau (CRS IPB) Corporate Plan and Investor Tracking System | The CRS IPB Corporate plan initiative will provide explicit and quantifiable impact objectives that relates directly to public development goals | 1. Engage the services of a consultant to: | Cross River State Investment Promotion Bureau improve its Corporate Plan and investor Tracking System to have competitive advantage | Cross River State Government, CRS Investment Promotion Bureau | CRS Investment Promotion Bureau | State Planning Commission, CRS Budget Department, Governor’s Office | Calabar Chambers of Commerce, Industry, Mineral and Agriculture (CALCIMA), Manufacturers Association of Nigeria (MAN) | 30000000 | January 10th 2025 | April 10th 2025 | COMPLETED: The CRS IPB Corporate plan initiative will provide explicit and quantifiable impact objectives that relates directly to public development goals | 1. Services of consultant engaged to: | The State Investment Promotion Bureau will continue to enagage relevant stakeholders to review and adopt a more robust Investment Promotion Corporate Plan
|  |  | · Review and upgrade CRS IPB Corporate Plan providing explicit and quantifiable impact objectives that defines clear FDI inflow projections and benefits in areas of expected number of job creation, revenue and social impact development. | [9 empty] | · Review and upgrade CRS IPB Corporate Plan providing explicit and quantifiable impact objectives that defines clear FDI inflow projections and benefits in areas of expected number of job creation, revenue and social impact development.
· Review and upgrade CRS IPB Investor Tracking Template from Micro Soft Excel Table format through installation of CRM software as an Investor Tracking System to enable CRS Investment Promotion Bureau keep track of relevant information on investors and build institutional memory.
|  |  | · Review and upgrade CRS IPB Investor Tracking Template from Micro Soft Excel Table format through installation of CRM software as an Investor Tracking System to enable CRS Investment Promotion Bureau keep track of relevant information on investors and build institutional memory. | [9 empty] | 2. Launching and adopteion of CRS IPB upgraded Corporate Plan and Investor Tracking System achieved
2. Launch and adopt CRS IPB upgraded Corporate Plan and Investor Tracking System
9 | Host two CRS Investment Promotion Bureau One Stop Investment Centre (CRS IPB OSIC) Stakeholders sensitization summit | This initiative will create awareness and foster synergy to newly establish parastatals and appointees in this present dispensation | 1. Identify newly establish parastatals and investment related appointees such as newly appointed members of CRS Land Use and Allocation Committee, Director General Cross River Geographic Information Agency (CRGIA), Surveyor General, amongst others. | Conduct advocacy meetings with target audience to foster synergy and reduce business entry turnaround time in the state | CRS Investment Promotion Bureau, OSIC MDAs, Cross River State Government, investors, Investors | CRS Investment Promotion Bureau | CRS Land Use Allocation Committee, Office of the State Surveyor General, CRS Geographic Information Agency, Ministry of Lands, Ministry of Industry, Ministry of Commerce, CRS Internal Revenue Service, Ministry of Transport, Ministry of Education, Ministry of Tourism, Ministry of Agriculture, Ministry of Local Government Affairs, Governor’s Office | Calabar Chambers of Commerce, Industry, Mineral and Agriculture (CALCIMA), Manufacturers Association of Nigeria (MAN) | 25000000 | February 3rd 2025 | February 10th 2025 | DELAYED This initiative will create awareness and foster synergy to newly establish parastatals and appointees in this present dispensation | 1. Adoption of desk officers from Cross River State Land Use and Allocation Committee, Cross River Geographic Information Agency (CRGIA) and Office of the Surveyor General into the One Stop Investment Centre (OSIC) delayed as a result of late preparation and signing of Memorandum of Understanding between Investment Promotion Bureau and Chief Executives of identified parastatals. | 1. Cross River State Investment Promotion Bureau One Stop Investment Centre stakeholder sensitization summit to introduce CRS OSIC framework and need for synergy with relevant government MDAs will be achieve by August 2026. 2. Adoption of new members as Desk Officers will be achieve by August 2026.
2. CRS IPB OSIC stakeholder sensitization summit to introduce CRS OSIC framework and need for synergy with relevant government MDAs delayed until Memorandum of Understanding is sign between Investment Promotion Bureau and Chief Executives of participating Ministries, Departments and Agencies.
2. Organize CRS IPB OSIC stakeholder sensitization summit to introduce CRS OSIC framework and need for synergy with relevant government MDAs.
3. Adoption of new members as desk officers delayed until signing of Memorandum of Understanding between Investment Promotion Bureau and Chief Executives of identified parastatals
3. Adopt new members as Desk Officers
10 | Host State Investment Incentive Review Summit | This initiative will enable the state to identify new incentives for regulation and adoption | 1. Obtain approval from the governor to host Cross River State Investment Incentive Review Summit to explore new areas where incentive can be introduced | Conduct advocacy meetings with government representatives and business community to identify and adopt sectorial incentives at state level | Cross River State Government, Investors, Organize private sector, general public | CRS Investment Promotion Bureau | CRS Internal Revenue Service, State Planning Commission, Governor’s Office, Ministries of Agriculture, Ministry of Local Government Affairs, State House of Assembly, Ministry of Transport | Calabar Chambers of Commerce, Industry, Mineral and Agriculture (CALCIMA), Manufacturers Association of Nigeria (MAN) | 25000000 | March 10th 2025 | March 25th 2025 | DELAYED This initiative will enable the state to identify new incentives for regulation and adoption | 1. This initiative is delayed due to late approval from the governor to host Cross River State Investment Incentive Review Summit to explore new areas where incentive can be introduced | 1. Hosting of Cross River State Investment Incentive Review Summit to explore new areas where incentive can be introduced to be achieve by August 2026
|  |  | 2. Identify and invite relevant stakeholders from public and private sector | [9 empty] | 2. Delay of approval by the governor to host the Cross River State Investment Incentive Review Summit delayed the identification and invitation of relevant stakeholders from public and private sector | 2. Identification and invitation of relevant stakeholders from public and private sector to be achieve by August 2026
|  |  | 3. Forward recommendations to the Governor for approval and possibly legislation by the legislature. | [9 empty] | 3. Delay of approval by the governor to host the Cross River State Investment Incentive Review Summit prolong the forwarding of recommendations to the Governor for approval and possibly legislation by the legislature. | 3. Recommendations will be presented to the Governor for approval and possibly legislation by the legislature by September 2026.
11 | Setup CRS Investment Promotion Bureau Investor Aftercare and retention program | The investor tracking system will provide a tool that enable Investment Promotion Bureau to keep track of relevant information on potential investors and build institutional memory | 1. Engage experts to develop CRS IPB Investor Aftercare and Retention Program strategic Framework that includes (i) criterion for prioritizing investors to receive aftercare and retention services; (ii) the main types of services to be provided to investors; and (iii) key performance indicators on aftercare and retention (minimally including: (a) number of investors supported with aftercare and retention services; (b) number of investor issues registered; and (c) number of investor issues resolved. | Setup an investor tracking mechanism in the Investment Promotion Bureau to keep vital records of existing investors | Cross River State Government, CRS Investment Promotion Bureau, Investors, general public | CRS Investment Promotion Bureau | Ministry of Science and Technology | Calabar Chambers of Commerce, Industry, Mineral and Agriculture (CALCIMA), Manufacturers Association of Nigeria (MAN) | 10000000 | February 2nd | December 10th 2025 | COMPLETED: The investor tracking system will provide a tool that enable Investment Promotion Bureau to keep track of relevant information on potential investors and build institutional memory | 1. Expert engaged to develop CRS IPB Investor Aftercare and Retention Program strategic Framework that includes (i) criterion for prioritizing investors to receive aftercare and retention services; (ii) the main types of services to be provided to investors; and (iii) key performance indicators on aftercare and retention (minimally including: (a) number of investors supported with aftercare and retention services; (b) number of investor issues registered; and (c) number of investor issues resolved. | The Cross River State Investment Promotion Bureau will continue to review and adopt investor friendly tracking system annually to serve potential investors professionally
|  |  | 2. Adopt and implement CRS IPB Investor Aftercare and retention program | [9 empty] | 2. Adoption and implementation of CRS IPB Investor Aftercare and retention program achieved
12 | Publish Fees, Procedures, Services delivery timelines, SLA and setup a GRM for 5 BEEs Minitries Departments and Agencies | This initiative will increase the number of CR State BEEs MDAs Fees, Procedures, Services delivery timelines, SLA and GRM on State portal from 8 to 13 on or before December 10th 2025. | 1. Identify more State BEEs to publish their Fees, Procedures, Services delivery timelines, SLA and setup a GRM 2. Develop and upload to state website - Fees, Procedures, Service Delivery Timelines, SLA and online GRM for CRS Ministry of Education, Ministry of Health, State Fire Service, Ministry of Agriculture and Ministry of Tourism | Publish Fees, Procedures, Service Delivery Timelines, SLA on State official website for public consumption and establish an office and appoint a desk officer whose phone number shall be made available to the public to receive complaints | Cross River State Government, General public, Organize private sector | Cross River State Enabling Business Environment Council Secretariat | CRS Ministry of Education, CRS Ministry of Health, State Fiore Service, Ministry of Agriculture, Ministry of Tourism, CRS Internal Revenue Service, Office of the Head of Service | Calabar Chambers of Commerce, Industry, Mineral and Agriculture (CALCIMA), Manufacturers Association of Nigeria (MAN) | 20000000 | March 5th 2025 | May 10th 2025 | DELAYED This initiative will increase the number of CR State BEEs MDAs -Fees, Procedures, Services delivery timelines, SLA and GRM on State portal from 8 to 13 on or before December 10th 2025. | 1. This initiative is delayed due to late submission of Fees, Procedures, Services delivery timelines, SLA and GRM contents by CRS Ministry of Education, Ministry of Health, State Fire Service, Ministry of Agriculture and Ministry of Tourism to the State Enabling Business Environment Secretariat. | 1. Development and uploading to state website - Fees, Procedures, Service Delivery Timelines, SLA and online GRM for CRS Ministry of Education, Ministry of Health, State Fire Service, Ministry of Agriculture and Ministry of Tourism to be achieve by September 2026
|  |  | 2. Set up functional Grievance Redress Mechanism Desk office for the above State MDAs within the MDAs to manage grievances | [9 empty] | 2. Uploading of Fees, Procedures, Service Delivery Timelines, SLA and online GRM for CRS Ministry of Education, Ministry of Health, State Fire Service, Ministry of Agriculture and Ministry of Tourism to the state website delayed due to late submission by identified parastatals. 3. Setting up of functional Grievance Redress Mechanism Desk office for the above State MDAs within the MDAs to manage grievances delayed due late submission of Fees, Procedures, Services delivery timelines, SLA and GRM contents by MDAs. | 2. Setting up of functional Grievance Redress Mechanism Desk office for CRS Ministry of Education, Ministry of Health, State Fire Service, Ministry of Agriculture and Ministry of Tourism to manage grievances will be achieve by September 2026
13 | Develop State and Local Government Consolidated Tax Payment Portal | This initiative will ensure that unique e-receipt is automatically generated and received by tax payers both at state and local government level for transparency and accountability | 1. Engage extensively with Chief Executives from State and local Government business related MDAs, State Board of Internal Revenue Service, Chairman of the 18 Local Governments Area and other stakeholders to ensure all fees, levies and taxes are harmonized into a demand notice. | Establish State and Local government consolidated tax payment portal that will generate automated e-receipt to all tax payers in the state in order to promote accountability | Cross River State Government, Local Government, investors, Organize private sector, General public | Cross River State Internal Revenue Service | Ministry of Local Government Affairs, Office of the State Accountant General, Office of State Auditor General, Local Government Auditor General Commission | Calabar Chambers of Commerce, Industry, Mineral and Agriculture (CALCIMA), Manufacturers Association of Nigeria (MAN) | 60000000 | January 10th 2025 | May 20th 2025 | COMPLETED: This initiative will ensure that unique e-receipt is automatically generated and received by tax payers both at state and local government level for transparency and accountability | 1. EngagIng extensively with Chief Executives from State and local Government business related MDAs, State Board of Internal Revenue Service, Chairman of the 18 Local Governments Area and other stakeholders to ensure all fees, levies and taxes are harmonized into a demand notice achieved | The State will continue to engage with relevant stakeholders to discover more quality approach on tax collection.
|  |  | 2. Upgrade Cross River State Internal Revenue Service existing online tax payment electronic platform to a Central Billing System enabling automatic E-receipt generation | [9 empty] | 2. Upgrading of Cross River State Internal Revenue Service existing online tax payment electronic platform to a Central Billing System enabling automatic E-receipt generation achieved
3. Implementation of the Cross River State Internal Revenue Service Central Billing System enabling automatic e-receipt upon payment achieved
3. Implement the Cross River State Internal Revenue Service Central Billing System enabling automatic e-receipt upon payment.
14 | Publish monthly performance reports for Small Claims Courts | This initiative will ensure that the public have access to Cross River State Small Claims Court Performance Reports from inception of CRS SCC to 30th March 2025 | 1. Ensure that Performance Reports from Cross River State two designated Small Claims Courts are generated and submitted by the assigned Magistrate monthly | CRS Judiciary shall publish monthly performance reports for small claims courts for easy accessibility | Cross River State Government, General Public | Cross River State Judiciary | Ministry of Science and Technology, CRS Enabling Business Environment Secretariat, Ministry of Justic | Calabar Chambers of Commerce, Industry, Mineral and Agriculture (CALCIMA), Manufacturers Association of Nigeria (MAN) | 5000000 | January 10th 2025 | May 10th 2025 | COMPLETED: This initiative will ensure that the public have access to Cross River State Small Claims Court Performance Reports from inception of CRS SCC to 30th March 2025 | 1.Performance Reports from Cross River State two designated Small Claims Courts are generated and submitted by the assigned Magistrate monthly | The State Judiciary will continue to generate and upload Small Claims Courts reports to the state judiciary website
2. All Report to Cross River State Judiciary website are uploaded
2. Upload report to Cross River State Judiciary website
517000000